## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-11 | Setup of project (JDK Spring boot) | MUST HAVE |  | Pravalika | 3-Completed
S1 | S1 | US-12 | Task CRUD using themeleaf UI | MUST HAVE | US-11 | Pravalika | 3-Completed
S1 | S1 | US-13 | Add filter sorting and paginalion in UI | MUST HAVE | US-12 | Pravalika | 3-Completed
S2 | S2 | US-21 | Add enums(Status priority) +UI improvement | MUST HAVE | US-12 | Pravalika | 3-Completed
S2 | S2 | US-22 | Implement REST APIs for Task CRUD | MUST HAVE | US-11 | Pravalika | 3-Completed
S2 | S2 | US-23 | Add REST filtering sorting and pagination | MUST HAVE | US-21 | Pravalika | 3-Completed
S2 | S2 | US-24 | API testing via postman + final checkup | MUST HAVE | US-22 | Pravalika | 3-Completed
S3 | S3 | US-31 | Authrntication and authorization | MUST HAVE | US-11 | Pravalika | 3-Completed
S3 | S3 | US-32 | integration of email Api | MUST HAVE | US-31` | Pravalika | 3-Completed
S3 | S3 | US-33 | Implementation session and jason web token | MUST HAVE | US-32 | Pravalika | 3-Completed
S4 | S4 | US-41 | Implementation of task tracking | MUST HAVE | US-12 | Pravalika | 3-Completed
S4 | S4 | US-42 | Build dashboard with visuals analytics | MUST HAVE | US-41 | Pravalika | 3-Completed
S4 | S4 | US-43 | Adding user profile and and password management | MUST HAVE | US-41 | Pravalika | 3-Completed
S4 | S4 | US-44 | Adding reminder settings export data | MUST HAVE | US-32 | Pravalika | 3-Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 63 | 5 | 5 | 5 | 4 | 4 | 5 | 4 | 5 | 5 | 5 | 5 | 3 | 0 | 0
SPRINT 1 BACKLOG
US-11 | T-1 | Downloading and installing JDK 17 ,Spring Boot Setup | 16/02/2026 | 18/02/2026 | Pravalika | Setting up | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-2 | Installing setting up intellij and setting up project enviroment | 19/02/2026 | 20/02/2026 | Pravalika | Setting up | Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-3 | Making TaskController and applying CRUD operation | 23/02/2026 | 25/02/2026 | Pravalika | coding | Completed | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-4 | Adding APIs pages for add,view,edit,delete and posting to github | 26/02/2026 | 27/02/2026 | Pravalika | coding | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0
US-12 | T-5 | Setting up Sql and connecting to spring boot | 2026-02-03 | 2026-03-03 | Pravalika | coding | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
US-13 | T-6 | Appling Pagination , filter and sorting | 2026-04-03 | 2026-05-03 | Pravalika | coding | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-21 | 0 | Adding enum's and working on css,html | 2026-08-03 | 2026-09-03 | Pravalika | coding | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-22 | T-8 | Adding RestController and Applying CRUD operation | 2026-09-03 | 2026-10-03 | Pravalika | coding | Completed | 5 | 0 | 0 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-23 | T-9 | Adding'Rest APIs pages for add,view,edit,delete | 2026-10-03 | 2026-11-03 | Pravalika | coding | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-23 | T-10 | Adding filter and sorting for Rest APIs | 2026-12-03 | 13/03/2026 | Pravalika | coding | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0
US-24 | T-11 | Api testing via postman | 16/03/2026 | 17/03/2026 | Pravalika | coding | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-24 | T-12 | Few api addition and UI improvement | 18/03/2026 | 20/03/2026 | Pravalika | coding | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-31 | T-13 | Adding Authcontroller | 20/03/2026 | 23/03/2026 | Pravalika | coding | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-32 | T-14 | Adding email service | 24/03/2026 | 25/03/2026 | Pravalika | coding | Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-32 | T-15 | Implementation sending and verifying oyp | 26/03/2026 | 27/03/2026 | Pravalika | coding | Completed | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-32 | T-16 | Working on Frontend of Authentication | 30/03/2026 | 31/03/2026 | Pravalika | coding | Completed | 4 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-33 | T-17 | Implementation sessions for taask viewing for respective accounts | 2026-01-04 | 2026-02-04 | Pravalika | coding | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
US-41 | T-18 | Implementing tracking systems based on status , priority and duedates | 2026-03-04 | 2026-06-04 | Pravalika | coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-42 | T-19 | Adding dashboard overview for tracking | 2026-06-04 | 2026-06-04 | Pravalika | coding | Completed | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-42 | T-20 | Working on Frontend for task overview and recent tasks | 2026-07-04 | 2026-07-04 | Pravalika | coding | Completed | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-43 | T-21 | Securing otp and password with bcrypt and adding security config | 2026-08-04 | 2026-08-04 | Pravalika | coding | Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-43 | T-22 | adding profile and editing profile details | 2026-09-04 | 2026-09-04 | Pravalika | coding | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-44 | T-23 | Adding reminder setting | 2026-10-04 | 2026-10-04 | Pravalika | coding | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-44 | T-24 | Adding calender view and improving visuals with list view and card view | 13/04/2026 | 13/4/2026 | Pravalika | coding | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0
US-44 | T-25 | Implementation export option through email and download option | 13/4/2026 | 13/04/2026 | Pravalika | coding | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 16/02/2026 | 27/02/2026 | Pravalika | improving the task management system |  | ui improvement | worked on add edit delete and filters and soritng
2 | Sprint 2 | 2026-02-03 | 13/3/2026 | Pravalika | implementation of REST API |  | testing | implemented REST controller and started testing
3 | Sprint3 | 16/03/2026 | 27/03/2026 | Pravalika | implementation of authentication and authorization |  | testing and verifying | providing user login signup options and making sure they work properly
4 | Sprint 4 | 30/03/2026 | 13/04/2026 | Pravalika | improment of ui and dashboard implementation |  | ui improvements | improving the ui and adding dashboard and remindert options
5
6
7